## Self evaluation
Kurssi ¦ Course |  |  |  | Pvm. ¦ Date
Machine Design Project |  |  |  | 25.4.2022
Ryhmän numero ¦ Group number
1
Aihe ¦ Topic
Blower cover
Ryhmän jäsenet ja työmäärä ¦ Group Members and Workload
Opiskelijanro Student No. | Nimi Name | Työmäärä * Workload | Kuittaus ** Concent
| Jakko | 34%
| Aaro | 39%
| Jakub | 27%
100%
* Arvioikaa, miten ryhmätyön työmäärä jakautui ryhmän jäsenten kesken. Jäsenten yhteistulos tulee olla 100%
** Jokaisen ryhmän jäsenen tulee hyväksyä ja sitoutua yhteiseen arvioon.
* Evaluate how the workload was distributed between group members. Total load has to equal 100%
** Every single group member has to ageree and concent this evaluation.
Ryhmän itsearviointi ¦ Group Self-Evaluation
Tässä onnistuimme ¦ These were our best achievements |  |  |  |  | Rivinvaihto ¦ New row: ALT+Enter
We have managed to fulfill the meets of Vesa and Valmet company. We have sucessfully finished the project, learn a ton of information about managing a mechanical engineering project and could try out our knowledge in the field. Learned to work under preassure and were able to deliver drawings even under a short period of time.
Nämä asiat olisimme voinut tehdä paremminkin ¦ These things we could have done better |  |  |  |  | Rivinvaihto ¦ New row: ALT+Enter
Stick more to the schedule. Be more proactive. We have been waiting for a special meeting at the very end to find a suitable box. This whole process could have been done by Vesa in a day or two and not needed to postpone the meeting and then getting it canceled after 10 days of waiting for it. Sricking more to the schedule and proactiviti from our side, other than that I do not see any markable downside. Maybe one more. Ensuring that all of us are working with the same solidworks version. It would make the last moments of the project way more stress free.
Palautetta opettajalle ¦ Feedback to the teacher |  |  |  |  | Rivinvaihto ¦ New row: ALT+Enter
I have only words of positivity to all the teaching stuff in JAMK so much support and helping students I have never seen. All the advice and suggestions during the process were on point. You were just a guard watching over us, but all the process was done by us. It made me feel as we have accomplished something. Thank you for the guidance, nothing than a words of praise.
Kyllä, tämä arvio pitää paikkansa.
Ei, en hyväksy ryhmän arviota.
Yes, this workload is correct.
No, I do not accept this group evaluation.